## Project Dashboard
COPELAND DESIGN STUDIO — PROJECT DASHBOARD
Copeland Group Services ¦ Engineering Design Toolkit
Current Version |  | v1.5
Version Name |  | Foundation + Drawing Pack
Status |  | ACTIVE
Current Sprint |  | Sprint 1 — Foundation
Sprint Start |  | 2026-06-26
Sprint End |  | 2026-07-10
Toolkit Owner |  | Copeland Group Services
Maintained By |  | PaulMc
SPRINT 1 — PROGRESS
Task | Status | Owner | Version
Project structure & folder system | COMPLETE | PaulMc | v1.0
Design Standards (DS-001) | COMPLETE | PaulMc | v1.0
CCTV Symbol Library (SL-001) | COMPLETE | PaulMc | v1.0
Drawing Templates spec (DT-001) | COMPLETE | PaulMc | v1.0
Survey Forms index (SF-001) | COMPLETE | PaulMc | v1.0
Camera Schedules (CS-001) | COMPLETE | PaulMc | v1.0
EcoWatch Designs (EW-001) | COMPLETE | PaulMc | v1.0
Event Security (ES-001) | COMPLETE | PaulMc | v1.0
Client Projects index (CP-001) | COMPLETE | PaulMc | v1.0
Design Manual (DM-001) | COMPLETE | PaulMc | v1.0
Master Workbook — Dashboard | COMPLETE | PaulMc | v1.5
Master Workbook — Backlog | COMPLETE | PaulMc | v1.5
Master Workbook — Kaizen Log | COMPLETE | PaulMc | v1.5
Master Workbook — Drawing Legend | COMPLETE | PaulMc | v1.5
Master Workbook — Release Notes | COMPLETE | PaulMc | v1.5
Engineering Drawing Sheet v1.5 | COMPLETE | PaulMc | v1.5
Client project folder template | COMPLETE | PaulMc | v1.5
CGS document numbering system | COMPLETE | PaulMc | v1.5
Smart Workbook — camera dropdowns | PLANNED | PaulMc | v1.6
Smart Workbook — auto numbering | PLANNED | PaulMc | v1.6
Smart Workbook — storage calc | PLANNED | PaulMc | v1.6
Smart Workbook — PoE budget | PLANNED | PaulMc | v1.6
Vector symbol library | PLANNED | PaulMc | v1.7
Full Design Manual v2.0 | PLANNED | PaulMc | v2.0

## Product Backlog
COPELAND DESIGN STUDIO — PRODUCT BACKLOG
All planned features, modules, and deliverables ¦ Maintained in version order
ID | Module | Deliverable | Version | Priority | Status | Effort | Notes | Owner
BL-001 | Design Standards | DS-001 Master Design Standards | v1.0 | High | COMPLETE | S |  | PaulMc
BL-002 | CCTV Symbols | SL-001 Symbol definitions (text) | v1.0 | High | COMPLETE | S |  | PaulMc
BL-003 | Drawing Templates | DT-001 Template specification | v1.0 | High | COMPLETE | S |  | PaulMc
BL-004 | Survey Forms | SF-001 Survey forms index | v1.0 | High | COMPLETE | S |  | PaulMc
BL-005 | Camera Schedules | CS-001 Schedule format + FoV data | v1.0 | High | COMPLETE | S |  | PaulMc
BL-006 | EcoWatch | EW-001 Sensor types + architecture | v1.0 | High | COMPLETE | S |  | PaulMc
BL-007 | Event Security | ES-001 Event security + Martyn's Law | v1.0 | High | COMPLETE | S |  | PaulMc
BL-008 | Client Projects | CP-001 Client project index + structure | v1.0 | High | COMPLETE | S |  | PaulMc
BL-009 | Design Manual | DM-001 Master reference manual | v1.0 | High | COMPLETE | M |  | PaulMc
BL-010 | Master Workbook | Project Dashboard sheet | v1.5 | High | COMPLETE | M |  | PaulMc
BL-011 | Master Workbook | Product Backlog sheet | v1.5 | High | COMPLETE | M |  | PaulMc
BL-012 | Master Workbook | Kaizen Log sheet | v1.5 | High | COMPLETE | S |  | PaulMc
BL-013 | Master Workbook | Drawing Legend sheet | v1.5 | High | COMPLETE | M |  | PaulMc
BL-014 | Master Workbook | Release Notes sheet | v1.5 | High | COMPLETE | S |  | PaulMc
BL-015 | Drawing Pack | Engineering drawing sheet v1.5 (HTML) | v1.5 | High | COMPLETE | L | A3 print-ready | PaulMc
BL-016 | Document Control | CGS document numbering system | v1.5 | High | COMPLETE | S | CGS-DS-001 format | PaulMc
BL-017 | Client Projects | Client project folder template (01-08) | v1.5 | High | COMPLETE | S |  | PaulMc
BL-018 | Smart Workbook | Camera type dropdown list | v1.6 | High | PLANNED | M | PTZ, Turret, Bullet etc | PaulMc
BL-019 | Smart Workbook | Automatic camera numbering (CAM-001) | v1.6 | High | PLANNED | M |  | PaulMc
BL-020 | Smart Workbook | Auto equipment totals | v1.6 | High | PLANNED | M |  | PaulMc
BL-021 | Smart Workbook | Bill of materials auto-generation | v1.6 | High | PLANNED | L |  | PaulMc
BL-022 | Smart Workbook | Storage calculation (GB/day per camera) | v1.6 | High | PLANNED | M | Based on CS-001 data | PaulMc
BL-023 | Smart Workbook | PoE power budget calculator | v1.6 | Med | PLANNED | M | Per switch, with headroom | PaulMc
BL-024 | Smart Workbook | Design validation checks | v1.6 | Med | PLANNED | L |  | PaulMc
BL-025 | Symbol Library | CCTV CAD block library (.dwg) | v1.7 | High | PLANNED | XL |  | PaulMc
BL-026 | Symbol Library | SVG symbol set (digital use) | v1.7 | High | PLANNED | L |  | PaulMc
BL-027 | Symbol Library | Intruder alarm symbol set | v1.7 | High | PLANNED | L |  | PaulMc
BL-028 | Symbol Library | Access control symbol set | v1.7 | High | PLANNED | L |  | PaulMc
BL-029 | Symbol Library | EcoWatch sensor symbols | v1.7 | Med | PLANNED | M |  | PaulMc
BL-030 | Symbol Library | Event security / HVM symbols | v1.7 | Med | PLANNED | M |  | PaulMc
BL-031 | Drawing Templates | A3 title block template (.dwg) | v2.0 | High | PLANNED | L |  | PaulMc
BL-032 | Drawing Templates | A1 drawing template (.dwg) | v2.0 | High | PLANNED | L |  | PaulMc
BL-033 | Survey Forms | SF-CCTV-001 CCTV survey (Word+PDF) | v1.2 | High | PLANNED | M |  | PaulMc
BL-034 | Survey Forms | SF-INT-001 Intruder survey (Word+PDF) | v1.2 | High | PLANNED | M |  | PaulMc
BL-035 | Survey Forms | SF-ACC-001 Access control survey | v1.2 | High | PLANNED | M |  | PaulMc
BL-036 | Survey Forms | SF-ECO-001 EcoWatch survey | v1.2 | Med | PLANNED | M |  | PaulMc
BL-037 | Survey Forms | SF-EVT-001 Event security survey | v1.2 | Med | PLANNED | M |  | PaulMc
BL-038 | Survey Forms | SF-MAR-001 Martyn's Law checklist | v1.2 | High | PLANNED | M |  | PaulMc
BL-039 | Survey Forms | SF-RISK-001 Security risk assessment | v1.2 | High | PLANNED | M |  | PaulMc
BL-040 | Design Manual | DM-001 Full manual v2.0 — all disciplines | v2.0 | High | PLANNED | XL |  | PaulMc

## Kaizen Log
COPELAND DESIGN STUDIO — KAIZEN LOG
Continuous improvement record — every change, every session
KAI-ID | Date | Version | Area | Improvement | Result | By | Session
KAI-001 | 2026-06-26 | v1.0 | Project Structure | Built complete 9-section CDS folder structure with master documents | Entire toolkit scaffolded and version-controlled from day one | PaulMc | Session 1
KAI-002 | 2026-06-26 | v1.0 | Design Standards | Created DS-001 with drawing numbering, line weights, colour coding, revision control | All future drawings follow a single consistent standard | PaulMc | Session 1
KAI-003 | 2026-06-26 | v1.0 | Camera Schedules | Added FoV reference tables and PoE budget rules to CS-001 | Engineers have quick reference data without external lookup | PaulMc | Session 1
KAI-004 | 2026-06-26 | v1.0 | Event Security | Martyn's Law tiers, HVM assets, throughput calc, and evacuation rules in ES-001 | Single source for all event security design decisions | PaulMc | Session 1
KAI-005 | 2026-06-26 | v1.5 | Document Numbering | Aligned numbering to CGS prefix (CGS-DS-001, CAM-001, SUR-001, PRJ-001) | Consistent numbering across all documents and drawings | PaulMc | Session 1
KAI-006 | 2026-06-26 | v1.5 | Master Workbook | Created Excel workbook with Dashboard, Backlog, Kaizen, Legend, Release Notes | Single source of truth for project status and planning | PaulMc | Session 1
KAI-007 | 2026-06-26 | v1.5 | Engineering Drawing | Created print-ready A3 HTML engineering drawing sheet with full title block | Professional drawing template ready to use for any project | PaulMc | Session 1
KAI-008 | 2026-06-26 | v1.5 | Client Projects | Created 01-08 subfolder structure for all client projects | Every project follows the same organised folder convention | PaulMc | Session 1

## Drawing Legend
COPELAND DESIGN STUDIO — DRAWING LEGEND
Standard symbol codes, descriptions and drawing colours for all Copeland Group Services drawings
Category | Code | Description | Drawing Colour | Line Type | Standard | Notes
CCTV | CAM-FX | Fixed camera (dome or bullet) | Red | Solid | BS EN 62676-4
CCTV | CAM-PT | Pan/Tilt camera | Red | Solid | BS EN 62676-4
CCTV | CAM-PTZ | Pan/Tilt/Zoom camera | Red | Solid | BS EN 62676-4
CCTV | CAM-DOM | Dome camera — vandal resistant | Red | Solid | BS EN 62676-4 | IK10
CCTV | CAM-BW | Body-worn camera | Red | Solid | BS EN 62676-4
CCTV | CAM-COV | Covert camera — pinhole | Red | Solid | BS EN 62676-4
CCTV | CAM-ANPR | ANPR / LPR camera | Red | Solid | BS EN 62676-4
CCTV | CAM-THM | Thermal imaging camera | Red | Solid | BS EN 62676-4
CCTV | NVR | Network Video Recorder | Red | Solid | BS EN 62676-4
CCTV | DVR | Digital Video Recorder | Red | Solid | BS EN 62676-4 | Analogue/HD-CVI
CCTV | SWITCH-POE | PoE Network Switch | Red | Solid | IEEE 802.3bt
Intruder | PIR | Passive Infrared Detector | Amber | Solid | BS EN 50131
Intruder | MCT | Magnetic Contact — door/window | Amber | Solid | BS EN 50131
Intruder | DT | Dual Technology Detector | Amber | Solid | BS EN 50131 | PIR+MW
Intruder | SB | Siren / Bell box — external | Amber | Solid | BS EN 50131
Intruder | CP | Control Panel | Amber | Solid | PD 6662
Intruder | KP | Keypad | Amber | Solid | PD 6662
Intruder | PB | Panic Button | Amber | Solid | BS EN 50131
Access | DR | Door Reader | Blue | Solid | BS EN 60839-11
Access | DC | Door Controller | Blue | Solid | BS EN 60839-11
Access | EL | Electromagnetic Lock | Blue | Solid | BS EN 60839-11
Access | RS | Request to Exit Sensor | Blue | Solid | BS EN 60839-11
Access | IC | Intercom — audio | Blue | Solid | BS EN 60839-11
Access | VIC | Video Intercom | Blue | Solid | BS EN 60839-11
EcoWatch | AQ-PM10 | PM10 Air Quality Sensor | Green | Solid | EA / LAQM.TG22
EcoWatch | AQ-NO2 | NO₂ Sensor | Green | Solid | EA / LAQM.TG22
EcoWatch | NV-LAEQ | Noise Monitor | Green | Solid | BS 4142
EcoWatch | MET-WND | Wind Speed / Direction | Green | Solid |  | Anemometer
EcoWatch | HYD-LEVEL | Water Level Sensor | Green | Solid
Event | Z-PUB | Public Zone boundary | Grey | Dashed | Martyn's Law
Event | Z-CON | Controlled Zone boundary | Blue | Solid | Martyn's Law
Event | Z-RES | Restricted Zone boundary | Amber | Solid | Martyn's Law
Event | Z-STE | Sterile Zone boundary | Red | Solid | Martyn's Law
Event | HVM | HVM barrier / bollard | Magenta | Solid | PAS 68 / IWA 14-1
Event | MUSTER | Assembly / Muster Point | Green | Solid
General | UPS | Uninterruptible Power Supply | Yellow | Solid | BS 7671
General | JB | Junction Box | Grey | Solid | BS 7671
General | CAT6 | Cat6 UTP cable route | Red (CCTV) | Dashed |  | Annotate discipline
General | FO | Fibre Optic cable route | Blue | Chain

## Release Notes
COPELAND DESIGN STUDIO — RELEASE NOTES
Version history and feature release record
Version | Date | Release Name | What's Included | Status | Owner
v1.0 | 2026-06-26 | Foundation | Initial build — project structure, 9 master documents, design standards, symbol library index, survey form index, camera schedule reference, EcoWatch, event security, client project index, design manual | RELEASED | PaulMc
v1.5 | 2026-06-26 | Foundation + Drawing Pack | Master Excel workbook (5 sheets), HTML engineering drawing sheet v1.5 (A3, print-ready), CGS document numbering alignment, client project 01-08 folder template, README and CHANGELOG updated | RELEASED | PaulMc
v1.6 | TBD | Smart Workbook | Camera type dropdowns, auto numbering (CAM-001), auto equipment totals, bill of materials, storage calculation, PoE power budget, design validation checks | PLANNED | PaulMc
v1.7 | TBD | Professional Drawing Sheet | Upgraded engineering drawing sheet, Copeland brand palette, premium title block, improved typography, print-ready A3 and A2 layouts | PLANNED | PaulMc
v1.2 | TBD | Survey Pack | All 7 survey forms as Word + PDF: CCTV, Intruder, Access Control, EcoWatch, Event Security, Martyn's Law, Security Risk Assessment | PLANNED | PaulMc
v1.1 | TBD | Symbol Library | Full graphical symbol library: CAD blocks (.dwg), SVG set, PDF reference sheet — CCTV, intruder, access, EcoWatch, event security | PLANNED | PaulMc
v2.0 | TBD | Copeland Design Studio | Full integrated platform: one workbook drives drawings + schedules + BOM + reports. Full Design Manual. Complete drawing template set A0-A4. | PLANNED | PaulMc